## Gantt Chart Template
STT | TASK TITLE | TASK CONTENT | TASK OWNER | START DATE | DUE DATE | DAYS | % TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | BÀI THỰC HÀNH 1 | Hoàn thành nội dung Thực hành 1 | Nguyễn Ngọc Linh | 2023-06-14 | 2023-06-15 | 1 | 100% | bar: WEEK 1 W
2 | BÀI THỰC HÀNH 2 | Hoàn thành nội dung Thực hành 2 | Phạm Vĩnh Khánh, Bùi Thị Mỹ Linh | 2023-06-21 | 2023-06-22 | 1 | 100% | bar: WEEK 2 W; WEEK 5 M
3 | BÀI THỰC HÀNH 3 | Hoàn thành nội dung câu 1 | Bùi Thị Mỹ Linh, Nguyễn Ngọc Linh | 2023-06-29 | 2023-06-30 | 1 | 100% | bar: WEEK 3 W
4 | BÀI THỰC HÀNH 3 | Hoàn thành nội dung câu 2, câu 3 | Phạm Vĩnh Khánh | 2023-06-29 | 2023-06-30 | 1 | 100% | bar: WEEK 3 W
5 | BÀI THỰC HÀNH 4 | Hoàn thành nội dung câu 1 | Bùi Thị Mỹ Linh, Nguyễn Ngọc Linh | 2023-07-05 | 2023-07-06 | 1 | 100% | bar: WEEK 4 W
6 | BÀI THỰC HÀNH 5 | Hoàn thành nội dung | Bùi Thị Mỹ Linh | 2023-07-19 | 2023-07-20 | 1 | 100% | bar: WEEK 6 W
7 | BÀI THỰC HÀNH 6 | Hoàn thành nội dung | Nguyễn Ngọc Linh | 2023-07-29 | 2023-07-29 | 1 | 100% | bar: WEEK 7 R
8 | BÀI THỰC HÀNH 7 | Hoàn thành nội dung | Phạm Vĩnh Khánh | 2023-08-09 | 2023-08-09 | 1 | 100% | bar: WEEK 8 W
9 | BÁO CÁO BÀI TẬP LỚN | Mô tả dữ liệu | Bùi Thị Mỹ Linh | 2023-06-29 | 2023-08-22 | 30 | 100%
|  | Chuẩn bị dữ liệu | Nguyễn Ngọc Linh
|  | Phân tích dữ liệu khám phá (EDA) | Phạm Vĩnh Khánh, Bùi Thị Mỹ Linh, Nguyễn Ngọc Linh
|  | Xây dựng mô hình | Phạm Vĩnh Khánh